## Development Status Report
Project Name | State | CBSA | Anchor Tenant | Anchor Opens | Est. Net Dev Costs After Partner Participation | Est. Net Costs to Complete (1) | Stabilized Yield | Completion Yield (2) | Completion Year Yield Qtr/Year | Company Owned GLA | Company Owned % Leased | Gross GLA | Gross % Leased
In-Process Dev Starts After 1/1/09:
Indio Towne Center-Babies/Toys | CA | Riverside-San Bernardino- Ontario | Babies "R" Us, Toys "R" Us | 2011-10-01 | 6001091 | 3796865.672 | 10.57% | 10.57% | Q4 - 2011 | 46827 | 100% | 46827 | 100%
Kent Place | CO | Denver-Aurora | King Soopers | 2012-10-01 | 8765009 | 4137940.35 | 9.316% | 9.302% | Q4 - 2013 | 47418 | 63.31% | 47418 | 63.31%
NorthGate Village | CO | Greeley | King Soopers | 2011-03-01 | 5405171.4505 | 1033131.8923 | 9.131% | 9.092% | Q4 - 2013 | 19376 | 5.295% | 139912 | 86.88%
Seminole Shoppes | FL | Jacksonville | Publix | 2010-09-01 | 15259116.25 | 1194969.29 | 9.832% | 9.832% | Q4 - 2011 | 73241 | 91.59% | 73241 | 91.59%
Market at Colonnade | NC | Raleigh-Cary | Whole Foods | 2011-03-01 | 15579217.2873 | 3164582.1016 | 9.07% | 9.07% | Q3 - 2012 | 57503 | 81.25% | 57503 | 81.25%
Shops at Stonewall Ph II | VA | Washington-Arlington- Alexandria | Dick's Sporting Goods | 2011-11-01 | 4995641 | 4580160 | 8.662% | 8.662% | Q4 - 2011 | 40670 | 100% | 40670 | 100%
Total In-Process Dev Starts After 1/1/09 |  |  |  |  | 56005245.9879 | 17907649.3059 | 9.434% | 9.427% |  | 285035 | 81.51% | 405571 | 87.01%
In-Process Dev Starts Prior to 1/1/09:
Shoppes at Fairhope Village | AL | Mobile | Publix | 2009-07-01 | 16671592.78 | 11906.65 | 7.077% | 5.743% | Q2 - 2012 | 84740 | 77.81% | 84740 | 77.81%
Applegate Ranch Shopping Center | CA | Merced | Wal-Mart, Target | 2008-08-01 | 37815400.46 | -419083.2315 | 5.027% | 3.406% | Q2 - 2011 | 144444 | 74.96% | 464136 | 92.21%
Golden Hills Promenade | CA | San Luis Obispo-Paso Robles | Lowe's | 2009-11-01 | 32392195.13 | 1287281.3716 | 4.431% | 3.717% | Q4 - 2012 | 216846 | 90.58% | 216846 | 90.58%
Indio Towne Center | CA | Riverside-San Bernardino- Ontario | WinCo Foods | 2008-09-01 | 41343122 | 1259316.5751 | 5.405% | 2.903% | Q4 - 2011 | 132678 | 59.03% | 368512 | 85.25%
Jefferson Square | CA | Riverside-San Bernardino- Ontario | Fresh & Easy | 2011-10-01 | 9356118.98 | -2016415.8713 | 5.51% | 2.698% | Q2 - 2012 | 38013 | 74.68% | 38013 | 74.68%
Paseo Del Sol | CA | Santa Barbara-Santa Maria- Goleta | Whole Foods | 2009-10-01 | 32439776.05 | 2409502.3398 | 6.43% | 6.43% | Q3 - 2012 | 49680 | 77.23% | 49680 | 77.23%
Plaza Rio Vista | CA | Riverside-San Bernardino- Ontario | Stater Bros. | 2008-05-01 | 18820953 | 449398.1529 | 7.214% | 4.024% | Q2 - 2011 | 67622 | 85.49% | 67622 | 85.49%
Centerplace of Greeley III | CO | Greeley | Best Buy, Sports Authority | 2008-09-01 | 16297150.15 | -1140768.76 | 8.143% | 5.827% | Q4 - 2011 | 94090 | 81.48% | 94090 | 81.48%
Shops at Quail Creek | CO | Boulder | King Soopers | 2009-05-01 | 7297975.4 | 265951.8831 | 11.42% | 10.97% | Q2 - 2012 | 37585 | 79.67% | 137429 | 94.44%
Caligo Crossing | FL | Miami-Fort Lauderdale- Miami Beach | Kohl's | 2008-10-01 | 6709433.74 | -25589.1357 | 8.118% | 8.118% | Q3 - 2011 | 10763 | 86.99% | 108928 | 98.71%
Nocatee Town Center | FL | Jacksonville | Publix | 2010-02-01 | 14203044.5406 | -4034496.8051 | 7.107% | 4.516% | Q1 - 2013 | 69679 | 88.03% | 69679 | 88.03%
Suncoast Crossing Ph I | FL | Tampa-St. Petersburg- Clearwater | Kohl's | 2008-10-01 | 8891779.5017 | -264575.41 | 6.477% | 3.179% | Q4 - 2011 | 108434 | 91.93% | 108434 | 91.93%
Suncoast Crossing Ph II | FL | Tampa-St. Petersburg- Clearwater | Target | 2009-08-01 | 7670561.6068 | 506440.24 | 2.989% | 1.69% | Q3 - 2012 | 9451 | 44.45% | 151649 | 96.54%
Walton Towne Center | KY | Cincinnati-Middletown | Kroger | 2008-11-01 | 6453406.4719 | -699864.1751 | 7.651% | 4.6% | Q4 - 2011 | 23186 | 81.89% | 139618 | 96.99%
Shops at Saugus | MA | Boston-Cambridge-Quincy | PetSmart, La-Z-Boy | 2008-08-01 | 35701401.25 | 457345.0461 | 6.643% | 6.268% | Q2 - 2011 | 90055 | 91.88% | 90055 | 91.88%
Village at Lee Airpark (f.k.a. Village at Lee Airport) | MD | Baltimore-Towson | Giant | 2010-11-01 | 23170959.1992 | 2149872.55 | 8.348% | 8.041% | Q4 - 2013 | 87548 | 91.52% | 87548 | 91.52%
State Street Crossing | MI | Ann Arbor | Wal-Mart | 2009-10-01 | 7792326.3531 | -1424736.8948 | 6.487% | 1.38% | Q2 - 2011 | 21049 | 60.01% | 168540 | 95.01%
Harris Crossing | NC | Raleigh-Cary | Harris Teeter | 2011-03-01 | 8361113.6861 | -1601458.672 | 6.967% | 6.366% | Q4 - 2012 | 65150 | 84.8% | 65150 | 84.8%
Deer Springs Town Center | NV | Las Vegas-Paradise | Target, Home Depot | 2009-03-01 | 82389005.24 | 2683916.7725 | 5.277% | 3.601% | Q1 - 2012 | 330907 | 89.31% | 463267 | 92.36%
Lower Nazareth Commons | PA | Allentown-Bethlehem- Easton | Target, Sports Authority | 2009-08-01 | 26932959.2196 | -882269.85 | 6.825% | 6.825% | Q3 - 2012 | 65367 | 97.55% | 198367 | 99.19%
Hickory Creek Plaza | TX | Dallas-Fort Worth- Arlington | Kroger | 2009-02-01 | 9875605.19 | 274676.7509 | 8.343% | 7.719% | Q4 - 2011 | 28134 | 77.6% | 109398 | 94.24%
Waterside Marketplace | TX | Houston-Baytown- Sugar Land | Kroger | 2009-10-01 | 5767370.8037 | 137228.8536 | 11.15% | 11.15% | Q4 - 2011 | 24858 | 92.55% | 147858 | 98.75%
Total In-Process Consolidated Dev Starts Prior to 1/1/09 |  |  |  |  | 456353250.7526 | -616421.62 | 6.307% | 4.875% |  | 1800279 | 83.8% | 3429559 | 91.49%
Canopy Oak Center | FL | Ocala | Publix | 2008-09-01 | 16899689.1976 | -1096806.4124 | 10.02% | 7.005% | Q3 - 2011 | 90041 | 77.82% | 90041 | 77.82%
Shoppes at Bartram Park - Phase III | FL | Jacksonville | Publix | 2004-10-01 | 2034206.1048 | -653144.0937 | 12.29% | 9.154% | Q1 - 2012 | 14639 | 30.1% | 33639 | 69.58%
Total In-Process Unconsolidated Dev Starts Prior to 1/1/09 |  |  |  |  | 18933895.3024 | -1749950.5061 | 10.26% | 7.229% |  | 104680 | 71.15% | 123680 | 75.58%
Total In-Process Developments |  | 30 |  |  | 531292392.0429 | 15541277.1799 | 6.767% | 5.415% |  | 2189994 | 82.9% | 3958810 | 90.54%
Completions:
Airport Crossing | IN | Chicago-Naperville-Joliet | Kohl's | 2007-10-01 | 2684960.3014 | -675067.3694 | 5.953% | 2.685% | Q1 - 2011 | 11924 | 77.79% | 101835 | 97.4%
Total Completed (4) |  | 1 |  |  | 2684960.3014 | -675067.3694 | 5.953% | 2.685% |  | 11924 | 77.79% | 101835 | 97.4%
Notes:
New starts for the quarter are in bold and shaded.
(1) Construction in progress (CIP) balance and costs to date on in-process developments are not equal. CIP balance contains costs of land held for development, deposits on contracts and other pre-closing costs.
(2) The yield at completion, no later than 3 years from last company owned anchor open date or 4 years from sitework start date.
(3) The NOI stabilized yield on costs above after allocating land basis for outparcel proceeds is estimated to be 6.3% (in-process) and 6.0% (completions).
(4) All completed projects are consolidated.